## RWT Plan Table of Contents
2025 RWT Plan Table Of Contents For TouchWorks EHR
General Information
Standards Update (Standards Version Advancement Process - SVAP)
Applicable Care Settings Defined
Justification for Real World Testing Approach
Measures Used in Overall Approach
Schedule of Key Milestones
Attestation
(c) Copyright Altera Digital Health LLC

## General Information
General Information
Category | Description | Version Numbers | Certified Health IT Product List (CHPL) ID
Plan Report ID Number | [For ONC-Authorized Certification Body Use Only]
Developer Name | Altera Digital Health
Product Name | TouchWorks EHR | 22.1.6 | 15.04.04.3123.Touc.22.09.1.231130
|  | 2024.1 | 15.04.04.3123.Touc.24.10.1.240506
Developer Real World Testing Page URL | https://www.alterahealth.com/legal/onc-reg-compliance/

## Standards Updates
Standards Version Advancement Process (SVAP) Updates Planned for 2025
Certification Criteria | Updated Standard | Certified Product | CHPL ID | Product ID Version | Method Used | Date Notification Sent to Drummond | Mandatory SVAP Disclosure Link | Date Notification Sent to Clients | Measure Used to Demonstrate Conformance with Updated Standard
§ 170.315(c)(3) - Clinical quality measures (CQMs) — report | CMS Implementation Guide for Quality Reporting Document Architecture: Category III ; Eligible Clinicians and Eligible Professionals Programs: Implementation Guide for 2024 (November 2023) | TouchWorks | 15.04.04.3123.Touc.22.09.1.231130 15.04.04.3123.Touc.24.10.1.240506 | 22.1.6 2024.1 | SVAP | SVAP Form Completed and emailed to Drummond on 10/28/2024 | https://www.alterahealth.com/legal/onc-reg-compliance/ | Updated annual specifications announced to clients via the Veradigm Compliance Reporting Solution (VCRS) v24.2 Release Notes published on 06/06/2024 and as part of a Client Webinar conducted on 11/14/2024 | Testing will be conducted as part of 170.315(c)(3) as outlined in the Measures Used in Approach tab.

## Applicable Care Settings Def
Applicable Care Setting | Explanation for Care Setting Inclusion
Multi-Specialty Outpatient | Segment to which we market and/or have deployed to providers employed by medical groups that are independently owned, non-academic, multi-specialty ambulatory (outpatient) practices. Multi-specialty groups represents a unique workflow compared to single specialty groups where the EHR configuration must simultaneously support a diverse set of medical and surgical subspecialties. The workflow is also quite different in that the single patient record is shared, updated and maintained across multiple users of multiple specialties.
Single Specialty Outpatient | Segment to which we market and/or have deployed to providers employed by medical groups that are independently owned, non-academic, single-specialty ambulatory (outpatient) practices. Single specialty groups represent specific workflows that best support their medical specialty and operate under different workflow demands of a multispecialty group or primary care. Single specialty groups often have specific challenges and varying perspectives on coordination of care activities and communication with referral entities.
Primary Care Outpatient | Segment to which we market and/or have deployed to providers employed by medical groups that are independently owned, non-academic, multi-specialty ambulatory (outpatient) practices. Primary care groups have unique challenges and workflow as they work to provide continuity of care across wellness, health maintenance and chronic disease management encounters. It is common in this care setting to have complex visits requiring providers to address acute illness, wellness reminder and chronic disease activities at a single visit. Primary care requires robust coordination of care activities across the care team and care settings. Primary Care specialties include family medicine, internal medicine, general obstetrics and gynecology (ob/gyn) or pediatrics.
Urgent Care | Segment to which we market and/or have deployed to providers employed by medical groups that are independently owned ambulatory practices that care for patients in an Urgent Care setting. These groups are not free standing or hospital based emergency departments and are typically open less than 24 hours a day. The urgent care setting is typically reimbursed similar to other outpatient (ambulatory centers); the workflow and sharing needs are often unique as they may be a single specialty group or typically part of a larger multi-specialty groups. Urgent care centers care for non-scheduled "walk in" type patients and are unique in that they provide episodic care and do not provide continuity of care.

## RWT Approach Justification
Justification for RWT Approach
Point-in-Time Testing: Use Case / Scenario-Based Testing | Description of testing plan | Simulated real world patient-focused scenarios and use cases will be utilized that exercise the features and functionalities of the EHR required by the certification criteria. In some cases, real world patient data will be used to confirm compliance with things such as successful transmission statuses for some interoperability certification criteria requirements. The use cases will include actions by varying user types to capture the required data and workflows. The steps of the patient-focused scenarios and use cases are cross-mapped to the individual requirements within the interoperability certification criteria to ensure complete testing. Compliance with required standards will be tested via manual inspection by experts from Altera and ONC-recommended test tools.
| Testing methods / methodologies | Any and all of the following test methodologies will be used to accomplish complete testing of conformance with the certification criteria requirements. While there will be a starting plan, the use of testing methodologies may vary based upon the individual client’s database set up, access to different EHR functionalities and skill sets of available client staff. - Manual entry of synthetic data - Screenshots of manually entered synthetic data and log files - Testing with ONC-approved testing tools, when appropriate - Analysis of EHR database log files - Analysis of external and Altera log files - Real world examples of successful transmissions by client report - Use of production environments when possible while limiting touchpoints with PHI as much as feasible - Use test and production environments as available
| Description of expected outcome | All clients will be able to successfully demonstrate the interoperability elements related to the certification criteria that will be tested.
| Justification for RWT Approach | - The RWT approach is intended to be laser-focused on demonstrating full compliance with the interoperable certification criteria requirements in a manner that provides the least burdensome work effort for clients to execute. - The testing scenarios will be performed in the client's Production database utilizing test patient or real patient data with PHI masked.
Ongoing Testing: Reporting Metrics by Certification Criterion | Description of testing plan | Aggregated metric data by certification criterion will be obtained from common/shared functionality managed by Veradigm for monthly reporting.
| Testing methods/methodologies | Veradigm Compliance Reporting Solution (VCRS): Collection of data for those clients connected to this solution to generate aggregated, montly data counts for CIRI and CCDA counts.
Allscripts Community Direct Messaging (ACDM): Veradigm (formerly Allscripts) team members will run and deliver aggregated reports on a monthly basis related to sending and receiving Direct messages
Registry Hub: (Source for inbound and outbound transmission of Registry messages to Public Health Agencies): Veradigm team members will run and deliver aggregated reports on a monthly basis related to inbound and outbound registry transactions
Rx Hub (Source for inbound and outbound transmission of eRx related messages to Surescripts): Veradigm team members will run and deliver aggregated reports on a monthly basis related to inbound and outbound electronic prescribing transactions.
API for FHIR R4 (source for API related metric counts) Veradigm team members will run and deliver aggregated reports on a monthly basis related to individual patient and multi-patient bulk requests.
| Description of expected outcomes by certification criterion | See Column E on Measures Used in Approach Tab
| Measurement/metric by certification criterion | See Column B on Measures Used in Approach Tab
| Justification for RWT Approach by certification criterion | See Column C on Measures Used in Approach Tab

## Measures Used in Approach
Touchworks Real World Testing Plan Across The Client Base
Certification Criteria | Planned Functional Testing / Reporting Metric Description | Justification | Applicable Care Settings | Expected Outcomes
POINT-IN-TIME FUNCTIONAL CONFORMANCE | Planned Functional Testing Description
Overall Point-in-Time Testing of Certification Criteria | Testing of certification criteria included in the certified product listings on the General Information tab. | To demonstrate the successful deployment of the certified functionality in real world environments. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | All clients representing the applicable Care Setting Types will be able to demonstrate the interoperability elements related to the certification criteria that will be tested to show that they work in the real world.
170.315(b)(1) Transitions of care and 170.315(h)(1) Direct Project | - Demonstration of creation of a C-CDA at the end of outpatient ambulatory encounter with transmission to the next provider of care via Direct Messaging with a confirmation of receipt. - Spot check of evidence of successful C-CDA transmissions in the client's production environment from the CCDA Queue. - Demonstration of the ability to receive a C-CDA via Direct messaging into the tasking inbox and save it into the EHR. -(b)(1) and (h)(1) use relied upon software from MedAllies in the ACDM Community Direct Messaging (ACDM) solution for the CCDA transmission process. ACDM is a component of the TouchWorks EHR ONC Certified IT Technology Package. | - To demonstrate the ability to send C-CDAs to the next provider of care via Direct Messaging upon ambulatory visit departure. - To demonstrate the ability to receive C-CDAs from external sources via Direct Messaging upon patient arrival for an ambulatory office visit, in transition or inbound referral. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | - Documentation evidencing receipt of C-CDAs into recipient EHRs when sent by the client via Direct Messaging MDN ACK notifications. - Documentation evidencing receipt of external C-CDAs into the client's EHR via Direct messaging into the tasking inbox with the user ability to save the C-CDA document to the patient's chart.
170.315(b)(2) CIRI | - Demonstration of problem list, medication list and allergy medication list reconciliation from discrete problems, medications and medication allergies parsed from a C-CDA. - Spot check of evidence of successful reconciliations of parsed discrete data in client production environment into the problem list, medication list and medication allergy list in the EHR. -(b)(2) uses relied upon software TouchWorks EHR ONC Certified Health IT Technology Package for receipt of the C-CDA. | To demonstrate the ability to reconcile discrete problems, medications and medication allergies parsed from a C-CDA into the EHR in a real-world environment. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the parsing of discrete problems, medications, and medication allergies from an inbound C-CDA with reconciliation of that data into the EHR problem list, medication list and medication allergy list.
170.315(b)(3) Electronic Prescribing | - Demonstration of creation and transmission of an electronic prescription in a client production system. - Spot check of evidence of successfully transmitted electronic new prescriptions in the client production environment via outbound message queues. -Spot check of evidence of the receipt and response for the following transactions (RxChangeRequest, RxChangeResponse; CancelRx, CancelRxResponse, RxRenewal Request, RxRenewal Response, RxFill, RxHistoryRequest, RxHistoryResponse) from the Inbound / Outbound message queues. | To demonstrate the ability to create and transmit electronic prescriptions successfully in a real-world environment. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | -Documentation evidencing the ability to create and transmit new electronic prescriptions as well as validate successful transmission of real-world prescriptions. -Documentation evidencing the ability to receive and respond to specific transactions from retail pharmacies.
170.315(b)(10) Electronic Health Information (EHI) Export | -Demonstration of the ability to create an export file(s) in a computable format with all of a single patient's EHI data without subsequent developer assistance to operate. -Demonstration of the ability to create an export file(s) in a computable format for a defined patient populations' EHI data which may require support on the part of the developer. -Demonstration of the ability to limit users who can create export file(s) | To demonstrate the ability to successfully export EHI data in a computable format for either a single patient or defined patient population on demand in a real-world environment. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | -Documentation evidencing the ability to create an export file(s) in a computable format with all of a single patient's EHI data without subsequent developer assistance to operate. -Documentation evidencing the ability to create an export file(s) in a computable format for a defined patient populations' EHI data which may require support on the part of the developer. -Documentation evidencing the ability to limit users who can create export file(s)
170.315(c)(1) Clinical quality measures – record and export | - Demonstration of the ability to export patient data recorded in the EHR and import that into the Veradigm Compliance Reporting Solution for calculation of a specified electronic clinical quality measure that will match the patient data recorded in the source EHR. - Demonstration of the ability to generate QRDA 1 files which comply with the CMS QRDA Implementation Guide without needing additional developer assistance or support. -(c)(1) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate that the calculation of quality measures out of the EHR Technology produces the same results when calculated by the Veradigm Compliance Reporting Solution tool and demonstrates the users ability to export quality measure data formatted in accordance with HL7 QRDA Category 1 standards. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability of the EHR to export and calculate electronic clinical quality measure data with user ability to export corresponding quality data without additional developer support.
170.315(c)(2) Clinical quality measures – import and calculate | - Demonstration of the ability to calculate quality measures for the patient population and measures specified in the demonstration for 170.315(c)(1) and match to the quality measure results obtained from the Veradigm Compliance Reporting Solution. -(c)(2) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate that the calculation of quality measures by the EHR produces the same results when they are calculated by the Veradigm Compliance Reporting Solution. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability of the EHR to export quality measure data used in achieving matching results in the demonstration for 170.315(c)(1) when quality measures are calculated by the Veradigm Compliance Reporting Solution.
170.315(c)(3) Clinical quality measures--report. | - Demonstration of the ability to generate QRDA 3 files which comply with the CMS QRDA Implementation Guide for selected electronic clinical quality measures. -(c)(3) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate that the EHR can produce QRDA Category 3 files acceptable for submission to CMS sponsored quality reporting programs. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing successful generation of QRDA Category 3 files that may be utilized for data submission to CMS sponsored quality reporting programs.
170.315(e)(1) View, download, and transmit to 3rd party. | Demonstration of the following capabilities: - Create and make a valid C-CDA available to the patient in the patient portal - Providing instructions on portal and API access via the patient portal invite process - Patient's ability to create a portal account and view their health information, including a C-CDA from their ambulatory visit. -Patient's ability to download and transmit a C-CDA from the portal via email transmission to any email address and via an encrypted method of electronic transmission. -(e)(1) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package and Allscripts FollowMyHealth. | To demonstrate the process for providing patient's with access to their health information via the patient portal as well as demonstrating the portal capabilities available to the patients. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability to provide access instructions to a patient to access their health information from a patient portal as well as availability of encounter related C-CDAs, including the ability to download and transmit these to a 3rd party.
170.315(f)(1) Transmission to public health agencies—immunization registry. | - Demonstration of the ability to generate a VXU message for an administered immunization and transmit it via HL7® 2.5.1 standard, the HL7® 2.5.1. IG IM Release 1.5, and July 2015 Addendum (HL7 22.5.1 standard) to a public health agency successfully. - Demonstration of the ability to receive, access and display the evaluated immunization history and forecast from an immunization registry for a patient in accordance with HL7® 2.5.1 standard. - Spot check of evidence in production environment of successful VXU message transmissions to a Public Health Agency. - Spot check of evidence in production environment of successfully received evaluated immunization history and forecast from a Public Health Agency. | To demonstrate the ability to submit and receive information on administered immunizations with a public health agency. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability to generate the VXU message for an administered immunization as well as the successful transmission to a public health agency via HL7 2.5.1. Documentation evidencing the ability for a user to request, access and display the evaluated immunization history and forecast from an immunization registry for a patient via HL7 2.5.1.
170.315(f)(2) Transmission to public health agencies—syndromic surveillance. | - Demonstration of the ability to generate a Syndromic Surveillance message for an urgent care patient and transmit it via HL7 2.5.1 to a public health agency successfully. - Spot check of evidence in production environment of successful Syndromic Surveillance HL7 message transmissions to a PHA. | To demonstrate the ability to submit information on subjective/objective status of urgent care patient on arrival to a public health agency. | • Urgent Care | Documentation evidencing the ability to generate the urgent care subjective/objective information on arrival as well as the successful transmission to a public health agency via HL7 2.5.1.
170.315(f)(4) Transmission to cancer registries | Demonstration of the ability to generate a Cancer Registry CDA for upload to Public Health Agency -(f)(4) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate of the ability to generate a Cancer Registry CDA for transmission to Public Health Agency | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability to generate a Cancer Registry CDA as well as the successful transmission to a Public Health Agency.
170.315(f)(5) Transmission to public health agencies - Electronic case reporting | -Demonstration of the ability to trigger and transmit an electronic case report CDA via Direct SMTP to the CDC AIMS platform. -Spot check of evidence in production environment from Tasking/Inbox of Reportability Reponses. -(f)(5) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate the ability to automatically generate and transmit an electronic case report CDA to a public health agency. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability to generate an electronic case reporting CDA as well as successful transmission to a public health agency via Direct SMTP to the CDC AIMS platform.
170.315(f)(7) Transmission to public health agencies – health care surveys. | Demonstration of the ability to generate a Health Care Survey CDA for upload to the CDC. -(f)(7) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate the ability to generate a Health Care Survey CDA for reporting to the CDC. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing the ability to generate a Health Care Survey CDA as well as the successful upload to the CDC, including client attestation of success.
170.315(g)(9) Application access – all data request. 170.315(g)(7) Application access – patient selection. | Demonstration of a patient's ability to make an all data request for a C-CDA via a 3rd party application that is connected to the EHR's FHIR R4 patient-facing API following authentication. -(g)(7) and (g)(9) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | To demonstrate the end-to end-functionality from when a patient makes a request for a C-CDA from a 3rd party application connected to the EHR, is authenticated and return of a C-CDA is received into the 3rd party application. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Documentation evidencing a patient's ability to request and retrieve a C-CDA from the EHR's FHIR R4 API into a 3rd party application in compliance with USCDI v1 and C-CDA R2.1.
170.315(g)(10) API - Standardized API for patient and population services 170.315(g)(7) Application access – patient selection. | -Demonstration of the ability to respond to a request for a single patient's data. -Demonstration of the ability to respond to a request for multiple patients' data. -(g)(10) uses relied upon software Veradigm Compliance Reporting Solution, which is a component of the TouchWorks EHR ONC Certified Health IT Technology Package. | -To demonstrate the end-to-end functionality for when an authorized patient makes a FHIR R4 data request using a 3rd party healthcare application of their choosing. -To demonstrate the end-to-end functionality for when an authorized user makes a FHIR R4 Bulk data request. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | -Documentation evidencing a single patient's ability to request and retrieve their own EHI data through FHIR R4 API. -Documentation evidencing an authorized user's ability to request and retrieve EHI data for multiple patients through FHIR R4 API.
ONGOING REPORT METRICS | Planned Reporting Metric Description
170.315(b)(1) Transitions of care and 170.315(h)(1) Direct Project | Total number of successfully transmitted C-CDAs (CCD and Referral Note) via Direct messaging based on receipt of MDN ACK message status | To demonstrate the volume of successfully transmitted C-CDAs via Direct messaging | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track volume of aggregated successful transmissions of C-CDAs via Direct Messaging by month.
| Total number failed C-CDA (CCD and Referral Note) transmissions based on receipt of MDN ACK message status | To quantify volume of unsuccessful C-CDA transmissions via Direct Messaging. Note that there are many reasons outside of the control of EHR vendors that can result in unsuccessful transmission. |  | Track volume of aggregated failed transmissions of C-CDAs via Direct Messaging by month.
| Total number received C-CDAs via inbound Direct messaging | To demonstrate the volume of successful receipt of C-CDAs via Direct Messaging into the tasking inbox. |  | Track volume of aggregated received transmissions of C-CDAs by month.
170.315(b)(2) CIRI | Total number of problem list reconciliations | To demonstrate the volume of completed problem list reconciliations performed. Note this metric is dependent upon client action. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track volume of aggregated problem list reconciliations by month
| Total number of medication list reconciliations | To demonstrate the volume of completed medication list reconciliations performed. Note this metric is dependent upon client action. |  | Track volume of aggregated medication list reconciliations by month
| Total number of medication allergy list reconciliations | To demonstrate the volume of completed medication allergy list reconciliations performed. Note this metric is dependent upon client action. |  | Track volume of aggregated medication allergy list reconciliations by month
| Total number with all 3 domains reconciled | To demonstrate the volume of completed reconciliations performed for problem list, medication list and allergy list. Note this metric is dependent upon client action. |  | Track volume of aggregated reconciliation of all three domains (problems, medications, medication allergies) by month
170.315(b)(3) Electronic Prescribing | Total number of new electronic prescriptions successfully transmitted | To demonstrate the volume of successfully transmitted electronic prescription messages. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track volume of aggregated successfully transmitted new electronic prescriptions by month
| Total number of changed electronic prescriptions successfully transmitted | To demonstrate the volume of successfully transmitted changed electronic prescription messages |  | Track volume of aggregated successfully transmitted changed electronic prescriptions by month
| Total number of canceled electronic prescriptions successfully transmitted | To demonstrate the volume of successfully transmitted canceled electronic prescription messages |  | Track volume of aggregated successfully transmitted canceled electronic prescriptions by month
| Total number of refill prescriptions successfully transmitted | To demonstrate the volume of the number of electronic prescription refills successfully transmitted. |  | Track volume of aggregated successfully transmitted electronic prescription refills by month
170.315(b)(10) Electronic Health Information Export | Total number of single patient exports of all health information that can be stored by TouchWorks for those patients, and the percentage of successful exports of a defined patient population of all electronic health information that can be stored by TouchWorks for those multiple patients obtained from volunteer testing clients. | To demonstrate the volume and success of Electronic Health Information Exports performed by our volunteer testing clients. |  | Track volume of successful performance of Electronic Health Information Exports by month for both single and multiple patients specific to our volunteer testing clients
170.315(c)(1) Clinical quality measures – record and export 170.315(c)(2) Clinical quality measures – import and calculate 170.315(c)(3) Clinical quality measures--report | Total QRDA 3 quality files generated for submission to MIPS program | To demonstrate volume of successful submission of QRDA files for MIPS reporting by Altera Health on behalf of clients. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregate of successful submission of QRDA files to CMS for 2024 reporting by month as follows: ECs - 1/2025 to 3/2025
170.315(e)(1) View, download, and transmit to 3rd party | Total number of C-CDA documents made available to patients via a patient portal | To demonstrate the volume of C-CDAs made available to patients associated to an encounter in an automated manner via the patient portal | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of C-CDAs made available to patients via the FMH by month
170.315(f)(1) Transmission to public health agencies—immunization registry | Total number of immunization registry HL7 message transmissions of administered immunizations | To demonstrate the volume of administered vaccines transmitted electronically to the appropriate public health agency | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of HL7 message transmissions of administered vaccines to state/regional Immunization Registries by month
| Total number of immunization registry HL7 query/response message transmissions | To demonstrate the volume of queries transmitted to immunization registries to obtain an evaluated immunization history and forecast |  | Track aggregated volume of HL7 query/response message transmissions by month
170.315(f)(2) Transmission to public health agencies—syndromic surveillance | Total number of Syndromic Surveillance HL7 message transmissions | To demonstrate the volume of syndromic surveillance electronic messages transmitted to the appropriate public health agency | • Urgent Care | Track aggregated volume of HL7 syndromic surveillance message transmissions to a state/regional registry by month
170.315(f)(4) Transmission to cancer registries | Total number of cancer registry CDA successful transmissions to public health agency | To demonstrate the volume of cancer registry CDA electronic messages transmitted to the appropriate public health agency | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of HL7 cancer message transmissions to a state/regional registry by month
170.315(f)(5) Transmission to public health agencies - Electronic case reporting | Total number of electronic case report CDAs successfully submitted via Direct SMTP to the CDC AIMS platform with MDN ACK message status. | To demonstrate the volume of electronic case reporting CDAs transmitted via Direct SMTP to the CDC AIMS platform. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of electronic case reporting CDA message transmissions via Direct SMTP to the CDC AIMS platform.
170.315(f)(7) Transmission to public health agencies – health care surveys | Total number of health care surveys CDAs successfully submitted via Direct messaging to CDC program with MDN ACK message status | To demonstrate the volume of Health Care Surveys transmitted to the CDC NHSN program | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of Health Care Summary CDAs to the CDC program by month
170.315(g)(7) Application access – patient selection 170.315(g)(9) Application access – all data request | Total number of patient API authentication events with all data requests (C-CDAs) received | To demonstrate the volume of patient C-CDA document requests via a third-party application based on FHIR R4 standards | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of patient requests for a full C-CDA via a patient-facing API by month
170.315(g)(7) Application access – patient selection. 170.315(g)(10) API - Standardized API for patient and population services | -Total number of data requests for a single patient's data. -Total number of data requests for multiple patients' data. | To demonstrate the volume of single patient requests for one or more data categories via a third party application. To demonstrate the volume of multiple patient requests for one or more data categories via a third party. | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | Track aggregated volume of single and multiple patient requests via either a patient-facing API third party application utilizing FHIR R4 or FHIR Bulk API.
EVENT COUNTING: Count monthly events based upon identified metric from midnight on the first day of the month to midnight on the last day of the month

## Schedule of Key Milestones
Testing Type | Key Milestone | Care Setting | Date/Timeframe
Point-in-Time Testing: Use Case / Scenario-Based Testing | Client recruitment | • Multi-Specialty Outpatient • Single Specialty Outpatient • Primary Care Outpatient • Urgent Care | 12/1/2024 to 01/31/2025
| Scheduling of each recruited client RWT project activities based on representative care setting ◼ Kick-off ◼ Review RWT project plan ◼ Establish RWT execution expectations and timeframes for touchpoint/status calls ◼ Establish agreed upon testing completion timeframes ◼ Determine need for client refresher training on certified functionality as required (i.e., Data Export functionality, etc.) |  | 1/1/2025 to 2/28/2025
| Conduct RWT activities over 6 to 8 week timeframe for each client ◼ Execution of RWT by client with Altera support for guidance/problem-solving ◼ Documentation of outcomes of RWT activities throughout testing process |  | 3/1/2025 to 6/30/2025
| Investigation of any client identified potential nonconformance during RWT activities |  | 3/1/2025 to 6/30/2025
| Review and analysis of output from individual client RWT outputs concurrently with client testing activities |  | 3/1/2025 to 6/30/2025
| Follow-up, clarification and retesting with client participants as required |  | 7/1/2025 to 8/31/2025
| Aggregation of all client RWT outputs into a final RWT Report section for Point-in-Time Testing |  | 9/1/2025 to 11/30/2025
Ongoing Testing: Reporting Metrics by Certification Criterion | Monthly reports provided by internal teams managing common/shared functionality as follows: ◼ Allscripts Community Direct Messaging (ACDM) ◼ Veradigm Rx Hub (for transmission of eRx messages inbound and outbound from Surescripts) ◼ Veradigm Registry Hub (for transmission of immunization registry messages inbound and outbound) ◼ Veradigm Compliance Reporting Solution (VCRS) ◼ FHIR R4 API |  | 1/1/2025 to 12/31/2025
| Monthly aggregation of reports from all sources |  | 2/1/2025 to 12/31/2025
| Monthly review and monitoring of aggregated report output from all sources |  | 2/1/2025 to 12/31/2025
| Preparation of final aggregated report output from all sources for inclusion in RWT Report |  | 1/1/2026 to 1/30/2026

## Attestation
Attestation Document