## RWT Plan Table of Contents
2025 RWT Plan Table Of Contents For Paragon
General Information
Standards Update (Including Standards Version Advancement Process - SVAP and USCDI
Applicable Care Settings Defined
Justification for Real World Testing Approach
Measures Used in Overall Approach
Schedule of Key Milestones
Attestation
(c) Copyright Altera Digital Health Inc.

## General Information
General Information
Category | Description | Version Numbers | Certified Health IT Product List (CHPL) ID
Plan Report ID Number | [For ONC-Authorized Certification Body Use Only]
Developer Name | Altera Digital Health
Product Names | Paragon® for Hospitals 2015 Cures Edition Certified EHR | 23.2 | 15.04.04.3123.Para.23.07.1.231205
| Paragon® Ambulatory Care 2015 Cures Edition EHR | 23.2 | 15.04.04.3123.Para.AM.08.1.231205
| Paragon® EHR | 24.1 | Pending
| Paragon® Denali EHR | 1.1 | Pending
Developer Real World Testing Page URL | https://www.alterahealth.com/legal/onc-reg-compliance/

## Standards Updates
No current standards have been updated under the Standards Version Advancement Process

## Applicable Care Settings Def
Applicable Care Setting | Explanation for Care Setting Inclusion
Acute | The primary marketing/advertising/sales approach for Paragon care settings is the use of one platform that supports the integration of acute and ambulatory configuration and workflows.
Critical Access Hospital
Ambulatory
Inpatient Rehabilitation Hospital | Paragon also supports additional content, configuration and workflows to support an Acute Rehabilitation care setting.

## RWT Approach Justification
Justification for RWT Approach
Point-in-Time Testing: Use Case / Scenario-Based Testing | Description of testing plan | Simulated real world patient-focused scenarios and use cases will be utilized that exercise the features and functionalities of the EHR required by the certification criteria. In some cases, real world patient data will be used to confirm compliance with things such as successful transmission statuses for some interoperability certification criteria requirements. The use case scenarios are cross-mapped to the individual requirements within the interoperability certification criteria to ensure complete testing.
| Testing methods / methodologies | Any and all of the following test methodologies will be used to accomplish complete testing of conformance with the certification criteria requirements. While there will be a starting plan, the use of testing methodologies may vary based upon the individual client’s database set up, access to different EHR functionalities and skill sets of available client staff. - Analysis of EHR database log files - Analysis of external and Altera log files - Real world examples of successful transmissions by client report - Use of production environments when possible while limiting touchpoints with PHI as much as feasible - Use test and production environments as available - Screenshots of manually entered data in the applications
| Description of expected outcome | All clients will be able to successfully demonstrate the interoperability elements related to the certification criteria that will be tested.
| Justification for RWT Approach | The RWT approach is intended to be focused on demonstrating full compliance with the interoperable certification criteria requirements in a manner that provides the least burdensome work effort for clients to execute. - The testing scenarios will be performed in the client's Testing database version that is a replication of their Production database version. Evidence collected will be augmented with actual production environment results wherever needed to support compliance analysis.
Ongoing Testing: Reporting Metrics by Certification Criterion | Description of testing plan | Aggregated metric data by certification criterion will be obtained from client live environments for monthly reporting.
| Testing methods/methodologies | Paragon Real World Testing Metrics: Deployment and configuration of a pre-specified report to run in an automated manner and transmit to a secure Altera site for an automated aggregation of monthly data.
| Description of expected outcomes by certification criterion | See Column E on Measures Used in Approach Tab
| Measurement/metric by certification criterion | See Column B on Measures Used in Approach Tab
| Justification for RWT Approach by certification criterion | See Column C on Measures Used in Approach Tab

## Measures Used in Approach
Paragon RWT Metrics to be Measured Across the Paragon Client Base
Certification Criteria | Planned Functional Testing / Reporting Metric Description | Justification | Applicable Care Settings | Expected Outcomes
POINT-IN-TIME FUNCTIONAL CONFORMANCE | Planned Functional Testing Description
Overall Point-in-Time Testing of Certification Criteria | Testing of certification criteria included in the certified product listings on the General Information tab. | To demonstrate the successful deployment of the certified functionality in real world environments. | The planned functional conformance testing defined in this table apply to all of the following Care Setting types: ◼ Acute ◼ Critical Access Hospital ◼ Ambulatory ◼ Inpatient Rehabilitation hospital | All clients representing the applicable Care Setting Types will be able to demonstrate the interoperability elements related to the certification criteria that will be tested to show that they work in the real world.
170.315(b)(1) Transitions of care and 170.315(h)(1) Direct Project | Demonstration of creation of a C-CDA at the end of an inpatient and ambulatory encounter with transmission to the next provider of care via Direct Messaging in a client testing environment that is a replica of production. Validate that there is a confirmation of receipt. - Spot check of evidence of successful C-CDA transmissions in the client's production environment from the Transmission Log. - Demonstration of the ability to receive a C-CDA via Direct messaging into the Inbox and attach it to a patient which saves it into Paragon's External Documents link. -(h)(1) uses relied upon software MedAllies for direct messaging | - To demonstrate the ability to send C-CDAs to the next provider of care via Direct Messaging upon inpatient discharge or ambulatory visit departure. - To demonstrate the ability to receive C-CDAs from external sources via Direct Messaging upon patient arrival as an admission, in transition or inbound referral. |  | - Documentation evidencing receipt of C-CDAs into recipient EHRs when sent by the client via Direct Messaging MDN ACK notifications. - Documentation evidencing receipt of external C-CDAs into the client's EHR via Direct messaging as an external document and save it into the EHR.
170.315(b)(2) CIRI | - Demonstration of problem list, medication list and allergy medication list reconciliation from discrete problems, medications and medication allergies parsed from a C-CDA in client testing environment that is a replica of production. - Spot check of evidence of successful reconciliations of parsed discrete data in client production environment into the problem list, medication list and allergy list in the EHR. | To demonstrate the ability to reconcile discrete problems, medications and medication allergies parsed from a C-CDA into the EHR in a real-world environment. |  | Documentation evidencing the parsing of discrete problems, medications, and medication allergies from an inbound C-CDA with reconciliation of that data into the EHR problem list, medication list and allergy list.
170.315(b)(3) Electronic Prescribing | - Demonstration of creation and transmission of an electronic prescription in a client testing environment that is a replica of production. - Spot check of evidence of successfully transmitted electronic prescriptions in the client production environment. -Spot check of evidence of the receipt and response for the following transactions (RxChangeRequest, RxChangeResponse; CancelRx, CancelRxResponse, RxRenewal Request, RxRenewal Response, RxFill) from the Inbound / Outbound message queues. -(b)(3) uses relied upon software Rcopia (DrFirst) | To demonstrate the ability to create and transmit electronic prescriptions successfully in a real-world environment. |  | Documentation evidencing the ability to create and transmit electronic prescriptions as well as validate successful transmission of real-world prescriptions.
170.315(b)(10) Electronic Health Information Export | Demonstration of successful EHI Export capability in a client testing environment that is a replica of production. | To demonstrate the ability to export all health information for a single patient and all health information for all patients. |  | Documentation evidencing the ability to export all health information for a single patient and all health information for all patients. Demonstrate the ability to get to the data definintion file.
170.315(e)(1) View, download, and transmit to 3rd party | Demonstration of the following capabilities: - Create and make a valid C-CDA available to the patient in the patient portal - Providing instructions on portal and API access via the patient portal invite process - Patient's ability to create a portal account and review their health information, including a C-CDA from their inpatient discharge and/or ambulatory visit. -(e)(1) uses relied upon software Veradigm FollowMyHealth | To demonstrate the process for providing patient's with access to their health information via the patient portal as well as demonstrating the portal capabilities available to the patients. |  | Documentation evidencing the ability to provide access instructions to a patient to access their health information from a patient portal as well as availability of encounter related C-CDAs.
170.315(f)(1) Transmission to public health agencies—immunization registry | - Demonstration of the ability to generate a VXU message for an administered immunization and transmit it via HL7 2.5.1 to a public health agency successfully. - Spot check of evidence in production environment of successful VXU message transmissions to a PHA. - Demonstration of the ability to transmit a request for and receive an immunization history | To demonstrate the ability to submit information on administered immunizations to a public health agency. |  | Documentation evidencing the ability to generate the VXU message for an administered immunization as well as the successful transmission to a public health agency via HL7 2.5.1. Documentation evidencing the ability to generate an immunization history and receive a response.
170.315(f)(2) Transmission to public health agencies—syndromic surveillance | - Demonstration of the ability to generate a Syndromic Surveillance message for an ED/Urgent care patient and transmit it via HL7 2.5.1 to a public health agency successfully. - Spot check of evidence in production environment of successful Syndromic Surveillance HL7 message transmissions to a PHA. | To demonstrate the ability to submit information on subjective/objective status of ED/urgent care patient on arrival to a public health agency. |  | Documentation evidencing the ability to generate the ED/urgent care subjective/objective information on arrival as well as the successful transmission to a public health agency via HL7 2.5.1.
170.315(f)(3) Transmission to public health agencies – reportable lab test/results (Inpatient) | - Demonstration of the ability to generate a Reportable Lab Result message and transmit it via HL7 2.5.1 to a public health agency successfully. - Spot check of evidence in production environment of successful Reportable Lab Result HL7 message transmissions to a PHA. | To demonstrate the ability to submit information on reportable lab results to a public health agency. |  | Documentation evidencing the ability to generate the Reportable Lab Result message as well as the successful transmission to a public health agency via HL7 2.5.1.
170.315(f)(5) Transmission to public health agencies – electronic case reporting. | - Demonstration of the ability to generate an Electronic Case Report CDA and transmit it via Direct messaging to the CDC AIMS platform. - Spot check of evidence in production environment from the Transmission Log. -Spot check of evidence in production environment from the eCR Inbox of Reportability Reponses and CDAs. | To demonstrate the ability to automatically generate and transmit an Electronic Case Report CDA to a public health agency and receive a Reportability Response from the PHA. |  | Documentation evidencing the ability to generate an Electronic Case Reporting CDA as well as the successful transmission to a public health agency via Direct messaging and successfully receive a Reportability Responses and CDAs.
170.315(f)(6) Transmission to public health agencies – antimicrobial use and resistance reporting. | Demonstration of the ability to generate a set of Antimicrobial Use & Resistance Reporting CDAs for transmission to the CDC NHSN platform. | To demonstrate the ability to generate a set of Antimicrobial Use & Resistance Reporting CDAs for reporting to the CDC NHSN platform. |  | Documentation evidencing the ability to generate a set of Antimicrobial Use & Resistance Reporting CDAs as well as the successful transmission to the CDC NHSN program.
170.315(g)(9) Application access – all data request. 170.315(g)(7) Application access – patient selection. | - Demonstration of a patient's ability to make an all data request for a C-CDA via a 3rd party application that is connected to EHR's patient-facing API following authentication. -(g)(7) and (g)(9) use relied upon software Microsoft Active Directory and one of Veradigm FollowMyHealth or Allscripts Health Connect | To demonstrate the end-to end-functionality from when a patient makes a request for a C-CDA from a 3rd party application connected to the EHR, is authenticated and return of a C-CDA is received into the 3rd party application. |  | Documentation evidencing a patient's ability to request and retrieve a C-CDA from the EHR's API into a 3rd party application.
170.315(g)(10) Standardized API for patient and population services. 170.315(g)(7) Application access – patient selection. | Demonstration of the ability to respond to a request for a single patient's data. - Demonstration of the ability to respond to a request for multiple patients' data according to the FHIR Bulk Standard. -(g)(10) use relied upon software Microsoft Active Directory and one of Veradigm FollowMyHealth or Allscripts Health Connect | To demonstrate the end-to end-functionality from when a patient makes a request for a C-CDA from a 3rd party application connected to the EHR, is authenticated and return of a C-CDA is received into the 3rd party application. To demonstrate the end-to end-functionality for when an authorized user makes a FHIR R4 Bulk data request and a response is provided. |  | Documentation evidencing a patient's ability to request and retrieve a C-CDA from the EHR's API into a 3rd party application. Documentation evidencing that a Bulk data request bungle was successfully returned.
ONGOING REPORT METRICS | Planned Reporting Metric Description
170.315(b)(1) Transitions of care and 170.315(h)(1) Direct Project | Percentage of successfully transmitted C-CDAs out of total number of transmitted C-CDAs | To demonstrate the volume of successfully transmitted C-CDAs via Direct messaging | The ongoing reporting metrics defined in this table apply to all of the following Care Setting types: • Acute • Critical Access Hospital • Ambulatory • Inpatient Rehabilitation Hospital | Identification of percentage of successful transmissions of C-CDAs via Direct Messaging by month.
| Percentage of inbound received C-CDAs for total inbound transitions, referrals and new patients | To demonstrate the volume of successful receipt of C-CDAs via Direct Messaging into Paragon's External Documents link. |  | Identification of percentage of received transmissions of C-CDAs by month.
170.315(b)(2) CIRI | Percentage of reconciliations where problems, medications and medication allergies from inbound received C-CDAs were completed | To demonstrate the volume of completed reconciliations performed. Note this metric is dependent upon client action. |  | Identification of percentage of finalized reconciliations (problems, medications, medication allergies) by month
170.315(b)(3) Electronic Prescribing | Percentage of new electronic prescriptions successfully transmitted out of all electronic prescribing transactions | To demonstrate the volume of successfully transmitted electronic prescription messages. |  | Identification of percentage of successfully transmitted new electronic prescriptions by month
| Percentage of changed electronic prescriptions successfully transmitted out of all electronic prescribing transactions | To demonstrate the volume of successfully transmitted changed electronic prescription messages |  | Identification of percentage of successfully transmitted changed electronic prescriptions by month
| Percentage of canceled electronic prescriptions successfully transmitted out of all electronic prescribing transactions | To demonstrate the volume of successfully transmitted canceled electronic prescription messages |  | Identification of percentage of successfully transmitted canceled electronic prescriptions by month
| Percentage of refill prescriptions successfully transmitted out of all electronic prescribing transactions | To demonstrate the volume of the number of electronic prescription refills successfully transmitted. |  | Identification of percentage of successfully transmitted electronic prescription refills by month
170.315(b)(10) Electronic Health Information Export | Percentage of successful single patient exports of all health information that can be stored by Paragon for those patients. | To demonstrate the volume of successful single patient Electronic Health Information Exports performed. |  | Ongoing monitoring of percentages of successful performance of Electronic Health Information Exports by month for single patients
170.315(e)(1) View, download, and transmit to 3rd party. | Percentage of C-CDA documents made available to patients via a patient portal for all combined inpatient discharges and clinic visits. | To demonstrate the volume of C-CDAs made available to patients in an automated manner via the patient portal |  | Ongoing monitoring of percentages of C-CDAs made available to patients via the patient portal
| Percentage of patients sent invites to create portal accounts for all unique patient discharges and clinic visits | To demonstrate the volume of invitations to patients to create a patient portal account |  | Identification of percentage of patient invites sent to patients for creation of a portal account by month
| Percentage of patient portal access events/logins for all unique patient discharges and clinic visits with active portal accounts | To demonstrate the total volume of successful patient access events/logins |  | Identification of percentage of patient portal login events by month
170.315(f)(1) Transmission to immunization registries. | Percentage of immunization registry HL7 message transmissions of administered immunizations successfully received by a PHA | To demonstrate the volume of administered vaccines transmitted electronically to the appropriate public health agency |  | Identification of percentage of HL7 message transmissions of administered vaccines to state/regional Immunization Registries by month
| Percentage of immunization registry HL7 responses received for queries transmited to an PHA | To demonstrate the volume of queries transmitted to immunization registries to obtain an evaluated immunization history and forecast |  | Identification of pecentage of HL7 query/response message transmissions by month
170.315(f)(2) Transmission to public health agencies—syndromic surveillance. | Percentage of Syndromic Surveillance HL7 message transmissions for ED/urgent care patients and ambulatory urgent care clinic visits successfully transmitted. | To demonstrate the volume of successful syndromic surveillance electronic messages transmitted to the appropriate public health agency |  | Identification of the percentage of successful HL7 syndromic surveillance message transmissions to a state/regional registry by month
170.315(f)(3) Transmission to public health agencies – reportable lab test/results | Percentage of successfully transmitted reportable lab results HL7 message transmissions to public health agency. | To demonstrate the volume of successful reportable lab results transmitted electronically to the appropriate public health agency |  | Identification of percentage of successful HL7 message transmissions for reportable lab results to a state/regional registry by month
170.315(f)(5) Transmission to public health agencies – electronic case reporting. | Percentage of electronic case report CDAs successfully transmitted via Direct messaging to AIMS as evidenced by the reportability response returned. | To demonstrate the volume of Electronic Case Reporting CDAs transmitted successfully via Direct messaging to the AIMS platform. |  | Identification of the percentage of Electronic Case Reporting CDAs successfuly transmitted to a state/regional registry by month
170.315(f)(6) Transmission to public health agencies – antimicrobial use and resistance reporting. INPATIENT ONLY | Percentage of AUR report CDAs successfully transmitted to the CDC NHSN program | To demonstrate the volume of AUR CDAs successfully transmitted to the CDC NSHN program |  | Ongoing monitoring of percentages for Antimicrobial Use and Resistance Reporting CDAs to the CDC NHSN program by month
170.315(g)(9) Application access – all data request. 170.315(g)(7) Application access – patient selection. | Percentage of all data requests (C-CDAs) received with completed responses. All data requests are dependent upon the patient authentication. | To demonstrate the volume of all data requests via a third-party application |  | Identification of percentage of patient requests for a full C-CDA via a patient-facing API by month
170.315(g)(10) Standardized API for patient and population services. 170.315(g)(7) Application access – patient selection. | Percentage of successful data category requests received with completed responses. Data category requests are dependent upon the patient authentication. | To demonstrate the volume of patient data category requests via a third-party application |  | Identification of percentage of patient data category requests via a patient-facing API by month
EVENT COUNTING: Count monthly events based upon identified metric from midnight on the first day of the month to midnight on the last day of the month

## Schedule of Key Milestones
Testing Type | Key Milestone | Care Settings | Date/Timeframe
Point-in-Time Testing: Use Case / Scenario-Based Testing | Client recruitment | ◼ Acute ◼ Critical Access Hospital ◼ Ambulatory ◼ Paragon Acute Rehabilitation hospital | 12/1/2024 to 3/1/2025
| Scheduling of each recruited client RWT project activities based on representative care setting ◼ Kick-off ◼ Review RWT project plan ◼ Establish RWT execution expectations and timeframes for touchpoint/status calls ◼ Establish agreed upon testing completion timeframes ◼ Determine need for client refresher training on certified functionality as required (i.e., Data Export functionality, etc.) |  | 1/1/2025 to 4/1/2025
| Conduct RWT activities over 6 to 8 week timeframe for each client ◼ Execution of RWT by client with Altera support for guidance/problem-solving ◼ Documentation of outcomes of RWT activities throughout testing process |  | 3/1/2025 to 7/30/2025
| Investigation of any client identified potential nonconformance during RWT activities |  | 3/1/2025 to 7/30/2025
| Review and analysis of output from individual client RWT outputs concurrently with client testing activities |  | 3/1/2025 to 7/30/2025
| Follow-up, clarification and retesting with client participants as required |  | 7/1/2025 to 8/31/2025
| Aggregation of all client RWT outputs into a final RWT Report section for Point-in-Time Testing |  | 9/1/2025 to 11/30/2025
Ongoing Testing: Reporting Metrics by Certification Criterion | Monthly reports provided by internal teams managing common/shared functionality as follows: ◼ Veradigm FollowMyHealth Patient Portal (for portal invites and patient actions in creating portal accounts and accessing portal data) |  | 1/1/2025 to 12/31/2025
| Monthly aggregation of reports from all sources |  | 2/1/2025 to 12/31/2025
| Monthly review and monitoring of aggregated report output from all sources |  | 2/1/2025 to 12/31/2025
| Preparation of final aggregated report output from all sources for inclusion in RWT Report |  | 1/1/2026 to 1/30/2026

## Attestation
Attestation Document
#VALUE!